## Project Planner
EPA2112 Societal Challenge Project
Legend: |  | Start |  | End
Activity | START | Duration | Week
|  |  | 1.6 | 1.7 | 1.8 | 1.9 | 1.10 | 2.1 | 2.2 | 2.3 | 2.4 | 2.5 | 2.6 | 2.7 | 2.8
Collecting data and interview input | 1.6 | 2 | bar: Week 1.6 to Week 1.7
Setting up solution, coding and constructing | 1.8 | 7 | bar: Week 1.8 to Week 2.3
Testing solution | 2.3 | 3 | bar: Week 2.3 to Week 2.5
Improving and finalizing solution | 2.4 | 4 | bar: Week 2.4 to Week 2.7
Documenting and preparing presentation | 2.6 | 3 | bar: Week 2.6 to Week 2.8
|  |  | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2022-01-10
Hour budget: | Max 14 hours per person per week.
13 weeks left with 5 persons. 5 * 13 * 14 = 910 hours total

## Blad1
Internship Erfgoed Leiden
Legend: | [5 empty] | Start week |  |  |  |  | End week | Duration
ACTIVITY | PLAN START | PLAN DURATION | WEEKS
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Finding literature | 1 | 5 | bar: WEEKS 1 to WEEKS 2
Browsing possibilities | 1 | 6 | bar: WEEKS 1
Reporting | 2 | 4 | bar: WEEKS 2
Goal 1: Displaying parcel location | 4 | 8 | bar: WEEKS 1
Goal 2: Making interactive map page | 4 | 2 | bar: WEEKS 2
Goal 3: Adding professions layer on map page | 4 | 3 | bar: WEEKS 4